## Task Data
SPRINT 2
Task to Complete During Sprint | Start Hours | Hours Spent Day 1 | Hours Spent Day 2 | Hours Spent Day 3 | Hours Spent Day 4 | Hours Spent Day 5 | Hours Spent Day 6 | Hours Spent Day 7 | Hours Spent Day 8 | Hours Spent Day 9 | Hours Spent Day 10 | Hours Spent Day 11 | Hours Spent Day 12 | Hours Spent Day 13 | Hours Spent Day 14
Create the login/signup page | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a user on signup (store in the database) | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Authenticate user input on signup | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Encrypt user password | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Authenticate user on login using tokens | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validate user login credentials | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the document area | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Send an HTTP request to loading the documents from the database | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design the profile page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 1 | 0 | 0.5
Create the buttons for adding new documents and courses | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
Display the documents which the user has already uploaded | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Create the navbar | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Create the brand name (NoteShare) for the navbar | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Create links for the various pages of the website | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Change the navbar depending if the user is signed in or not | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Create a section that allows a user to add a course | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Send an http request to the server with user and course information | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Store the course in the database base and associate it to the user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Create a splash section to greet the user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Create an about section | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Create a footer | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create sidebar | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Send an HTTP request to load courses from the database | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allow user to select a course for which they like to view courses for | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Remaining effort | 38 | 38 | 24 | 24 | 24 | 24 | 24 | 21 | 21 | 20.5 | 20.5 | 20.5 | 14.5 | 14.5 | 8
Ideal burndown | 38 | 35.2857 | 32.5714 | 29.8571 | 27.1429 | 24.4286 | 21.7143 | 19 | 16.2857 | 13.5714 | 10.8571 | 8.1429 | 5.4286 | 2.7143 | -1.1546e-14
Number of Tasks Remaining | 24 | 24 | 18 | 18 | 18 | 18 | 18 | 17 | 17 | 17 | 17 | 17 | 12 | 12 | 6
Completed Tasks | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 6
SPRINT 3
Task to Complete During Sprint | Start Hours | Hours Spent Day 1 | Hours Spent Day 2 | Hours Spent Day 3 | Hours Spent Day 4 | Hours Spent Day 5 | Hours Spent Day 6 | Hours Spent Day 7 | Hours Spent Day 8 | Hours Spent Day 9 | Hours Spent Day 10 | Hours Spent Day 11 | Hours Spent Day 12 | Hours Spent Day 13 | Hours Spent Day 14 | Hours Spent Day 15 | Hours Spent Day 16 | Hours Spent Day 17 | Hours Spent Day 18 | Hours Spent Day 19 | Hours Spent Day 20 | Hours Spent Day 21
US-08: Adding Courses (4)
Create a section that allows a user to add a course | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Send an http request to the server with user and course information | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
Create a course table in the database and link it to user | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a folder for the course to store the documents inside | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Store the course in the database base and associate it to the user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11: Homepage (1)
Create an about section | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a footer | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03: Downloading Documents (7)
Create a download button that allows users to receive a document | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
Create a HTTP request to request the document to be downloaded | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create api route to send file to the client | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Initiate the download on the client side | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-02: Uploading Documents (8)
Create an upload button to allow users to send documents to the server | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a http request to upload a pdf document | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Receive the pdf on the server | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process the pdf for storage | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Link documents to user and course | 2 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Store the pdf in an appropriate place on the server | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US-14: Comment Area (6)
Create a text area where users can write their comment | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Have a section where users can see the comments already on a document | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Indicate to the user which document they are commenting on | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Style the comment area so it looks nice for the user | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
Remaining effort | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 24 | 24 | 22 | 22 | 21 | 21 | 21 | 13.5 | 13.5 | 13 | 13 | 13 | 13 | 13 | 4.5 | 4.5 | 0
Ideal burndown | 31.5 | 31.5 | 30 | 28.5 | 27 | 25.5 | 24 | 22.5 | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5
Number of Tasks Remaining | 21 | 21 | 21 | 21 | 21 | 19 | 19 | 18 | 18 | 17 | 17 | 17 | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 3 | 3 | 0
Completed Tasks | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 3
SPRINT 4
Task to Complete During Sprint | Start Hours | Hours Spent Day 1 | Hours Spent Day 2 | Hours Spent Day 3 | Hours Spent Day 4 | Hours Spent Day 5 | Hours Spent Day 6 | Hours Spent Day 7 | Hours Spent Day 8 | Hours Spent Day 9 | Hours Spent Day 10 | Hours Spent Day 11 | Hours Spent Day 12 | Hours Spent Day 13 | Hours Spent Day 14
US-19: Deleting Documents (6)
Create font-end button to delete document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Style front-end section | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Send a http request with document to delete | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Delete document on the server | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-18: Profile Editing (7)
Create font-end button and editing view | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Style the front end views | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Send http request with new data to the server | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Update the database with new information | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-17: User Role (3)
Create font-end section for dropdown | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Style front-end section | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add verification on the server | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Add role attribute to user | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Load the role on the profile | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-16: Profile Biography (2)
Create font-end section for the biography | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Style front-end section of the biography | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add biography attribute to user object in the database | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Create http request to load biography from server | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
US-15: Profile Statistics (4)
Determine statistics criteria | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create front-end list or table to hold statistics | 3 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 2 | 0 | 0 | 0.5 | 0 | 0
Style the front-end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
Create backend api routes for the needed data | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Create http requests to load data onto the frontend | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-05: Censoring Comments (5)
Decide which words should be sensored | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use a library or a regex pattern to sensor the users comment before it is save to the database | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-04: Leaving Comments on Documents (8)
Send a HTTP request to load comments from the database that already on a document | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Send a HTTP request to send comments to save in the database | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Associate comments to a document and user | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Always make comments scroll to bottom | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Update comments with new comment | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Remaining effort | 35 | 35 | 35 | 35 | 35 | 30.5 | 30.5 | 25.5 | 25.5 | 21.5 | 21.5 | 21.5 | 10 | 10 | 0
Ideal burndown | 35 | 32.5 | 30 | 27.5 | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
Number of Tasks Remaining | 29 | 29 | 29 | 29 | 29 | 25 | 25 | 22 | 22 | 20 | 20 | 20 | 8 | 8 | 0
Completed Tasks | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 2 | 0 | 0 | 12 | 0 | 8
SPRINT 5
Task to Complete During Sprint | Start Hours | Hours Spent Day 1 | Hours Spent Day 2 | Hours Spent Day 3 | Hours Spent Day 4 | Hours Spent Day 5 | Hours Spent Day 6 | Hours Spent Day 7 | Hours Spent Day 8 | Hours Spent Day 9 | Hours Spent Day 10 | Hours Spent Day 11 | Hours Spent Day 12 | Hours Spent Day 13 | Hours Spent Day 14
US-21: Delete a Joined Course from Profile (6)
Add a delete function to the courses route. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add a button in the view to leave a course you are a member of. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Connect the route to the view. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-22: Rename Uploaded Documents (7)
Create an api end route to update the document name | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build the form on the front end to edit the name | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Connect the view to the route | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-06: New Document Notifications (9)
Decide on the external service to use | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Integrate the external service into the application | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
Send the notification | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-AC: Unit Testing (10)
unit tests | 20 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 5 | 0 | 0 | 5 | 0 | 5
US-AB: Documentation (10)
keeping track of all the meeting minutes and slack conversations | 3 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5
Remaining effort | 36 | 36 | 34.5 | 34.5 | 34.5 | 32 | 32 | 27.5 | 27.5 | 22 | 22 | 22 | 5.5 | 5.5 | 0
Ideal burndown | 36 | 33.4286 | 30.8571 | 28.2857 | 25.7143 | 23.1429 | 20.5714 | 18 | 15.4286 | 12.8571 | 10.2857 | 7.7143 | 5.1429 | 2.5714 | -6.2172e-15
Number of Tasks Remaining | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 2 | 2 | 0
Completed Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 7 | 0 | 2